## GLOBE NLZ
| Customer Site ID | DU ID | DU Name | SITENAME | SITE NAME | DENIRO NAME | LAT | LONG | TowerCo | RAAWAA STATUS | TOWERCO DURATION | TOWERCO ACCESS STATUS | PROVINCE | SITE ADDRESS | TOWN | TEAM LEADER | CONFIRMED/NOT CONFIRMED | PO | MOS DATE | INSTALLATION DATE | DATE FINISHED | RPAT/PAT DATE | REMARKS
| NL596 | NL596_EOS_WL | TCMCRPULONGGUBATBLGTASBUL_EOS_WL | SAMOL |  |  | 14.8583 | 120.9061 | MIDC |  |  |  | BULACAN | Pulong Gubat, Balagtas (Ibaba), Bulacan | BALAGTAS (IBABA) |  | CONFIRMED
| NL596 | NL596_G9_WL_TRX Downgrade | TCMCRPULONGGUBATBLGTASBUL_G9_WL_TRX Downgrade | SAMOL |  |  | 14.8583 | 120.9061 | MIDC |  |  |  | BULACAN | Pulong Gubat, Balagtas (Ibaba), Bulacan | BALAGTAS (IBABA) |  | CONFIRMED
| NL1375 | NL1375_900MRRUChangeout_WL | TCFGACATANGHALANOBANDOBUL_900MRRUChangeout_WL | OBANDOSTH |  |  | 14.7059 | 120.9421 | FTAP |  |  |  | BULACAN | #9 Sevilla St, Catanghalan, Obando, Bulacan | OBANDO |  | NOT CONFIRMED
| NL1719 | NL1719_EOS_WL | SAPAMARIA_EOS_WL | SAPAMARIA |  |  | 14.8789 | 120.981 | FTAP |  |  |  | BULACAN | Lot 303, Mag-asawang Sapa, Santa Maria, Bulacan | SANTA MARIA |  | CONFIRMED
| NL1895 | NL1895_EOS_WL | TCMCRPINAGBARILANBLIUAGBUL_EOS_WL | PNAGBARIL |  |  | 14.9532 | 120.8768 | MIDC |  |  |  | BULACAN | Pinagbarilan, Baliuag, Bulacan | BALIUAG |  | NOT CONFIRMED
| NL2230 | NL2230_1800MDismantling_WL | PH6ARENAID_1800MDismantling_WL | PH6ARENAID |  |  | 14.7935 | 120.9535 | GT BAU |  |  |  | BULACAN | Philippine Arena, Ciudad de Victoria, Bolacan, Bocaue, Bulacan | BOCAUE |  | CONFIRMED
| NL2760 | NL2760_EOS_2023_WL | UPPERQUARRYSJDMBUL_EOS_WL | UPPERQUARRYSJDMBUL |  |  | 14.8431 | 121.091 | MIDC |  |  |  | BULACAN | Santo Niño, San Jose Del Monte, Bulacan | SAN JOSE DEL MONTE |  | NOT CONFIRMED
| NL306 | NL306_EOS_WL | DALANDEST_EOS_WL | DALANDEST |  |  | #N/A | #N/A | MIDC |  |  |  | BULACAN | #N/A | #N/A |  | NOT CONFIRMED
| NL312 | NL312_EOS_WL | TCFGASANIGNACIOSTSJDMBUL_EOS_WL | SANIGNACIOSTSJDMBUL |  |  | 14.8115 | 121.0419 | FTAP |  |  |  | BULACAN | Lot 287, Sitio Pangitlugan, San Ignacio, Muzon, San Jose Del Monte, Bulacan | SAN JOSE DEL MONTE |  | NOT CONFIRMED
| NL305 | NL305_700M+900MRRUChangeout_WL | TCFGATIBAGANBUSTOSBUL_700M+900MRRUChangeout_WL | TIBAGAN |  |  | 14.9524 | 120.9472 | FTAP |  |  |  | BULACAN | Cruz Compound, Tibagan, Bustos, Bulacan | BUSTOS |  | NOT CONFIRMED
| NL319 | NL319_EOS_WL | TCFGAMALAWAKBUSTOSBUL_EOS_WL | BUSTOSSTH |  |  | 14.9104 | 120.9496 | FTAP |  |  |  | BULACAN | Purok III, 22 Narra St., Malawak, Bustos, Bulacan | BUSTOS |  | NOT CONFIRMED
| NL541 | NL541_1800MDismantling_WL | TCFGABUGUIONCLUMPTBUL_1800MDismantling_WL | HBROXAS |  |  | 14.8967 | 120.795 | FTAP |  |  |  | BULACAN | Buguion, Calumpit, Bulacan | CALUMPIT |  | NOT CONFIRMED
| NL542 | NL542_EOS_WL | TCFGASANISDROSJDMBUL_EOS_WL | SANISDROSJDMBUL |  |  | 14.8239 | 121.1303 | FTAP |  |  |  | BULACAN | San Isidro, San Jose Del Monte, Bulacan | SAN JOSE DEL MONTE |  | NOT CONFIRMED
| NL542 | NL542_G18_WL_TRX Downgrade | TCFGASANISDROSJDMBUL_G18_WL_TRX Downgrade | SANISDROSJDMBUL |  |  | 14.8239 | 121.1303 | FTAP |  |  |  | BULACAN | San Isidro, San Jose Del Monte, Bulacan | SAN JOSE DEL MONTE |  | NOT CONFIRMED
| NL543 | NL543_EOS_WL | MALOLOS_EOS_WL | MALOLOS |  |  | 14.8432 | 120.8049 | GT BAU |  |  |  | BULACAN | Hipolito cor Soliman Sts, Caingin, Malolos, Bulacan | MALOLOS CITY (CAPITAL) |  | CONFIRMED
| NL552 | NL552_EOS_WL | TCMCRTABONPULILBUL_EOS_WL | PULILAN |  |  | 14.9141 | 120.8331 | MIDC |  |  |  | BULACAN | Tabon, Pulilan, Bulacan | PULILAN |  | NOT CONFIRMED
| NL558 | NL558_700M+900MRRUChangeout_WL | TCFGAFRANCISCOHOMESJDMBUL_700M+900MRRUChangeout_WL | FRANCISCOHOMESJDMBUL |  |  | 14.8098 | 121.0635 | FTAP |  |  |  | BULACAN | Danang Building, Francisco Homes-Mulawin, San Jose Del Monte, Bulacan | SAN JOSE DEL MONTE |  | NOT CONFIRMED
| NL566 | NL566_EOS_WL | TCMCRLIBISRAFAELBUL_EOS_WL | SNRAFATWN |  |  | 14.9591 | 120.9687 | MIDC |  |  |  | BULACAN | Estrella St., Libis, San Rafael, Bulacan | SAN RAFAEL |  | NOT CONFIRMED
| NL572 | NL572_700M+900MRRUChangeout_WL | POBLACION2MRILAOBUL_700M+900MRRUChangeout_WL | POBLACION2MRILAOBUL |  |  | 14.7618 | 120.9479 | GT BAU |  |  |  | BULACAN | Constantino St., Abangan Sur, Marilao, Bulacan | MARILAO |  | CONFIRMED
| NL582 | NL582_EOS_WL | TCFGAKAYBANBANSJDMBUL_EOS_WL | KAYBANBANSJDMBUL |  |  | 14.8086 | 121.0898 | FTAP |  |  |  | BULACAN | 29 Tanghali Road, Kaybanban, San Jose Del Monte, Bulacan | SAN JOSE DEL MONTE |  | NOT CONFIRMED
| NL583 | NL583_700M+900MRRUChangeout_WL | TCMCRGRACEVILLESJDMBUL_700M+900MRRUChangeout_WL | GRACEVILLESJDMBUL |  |  | 14.7858 | 121.0639 | MIDC |  |  |  | BULACAN | Dama de Noche St., Graceville, San Jose Del Monte, Bulacan | SAN JOSE DEL MONTE CITY |  | NOT CONFIRMED
| NL585 | NL585_EOS_WL | TCFGAMEYTOCLUMPTBUL_EOS_WL | HAGONYNTH |  |  | 14.8791 | 120.7282 | FTAP |  |  |  | BULACAN | 111, Meyto, Calumpit, Bulacan | CALUMPIT |  | NOT CONFIRMED
| NL586 | NL586_EOS_WL | TCFGASANJOSEPAOMBOBUL_EOS_WL | PAOMBONG |  |  | 14.8279 | 120.7912 | FTAP |  |  |  | BULACAN | San Jose Road, San Jose, Paombong, Bulacan | PAOMBONG |  | NOT CONFIRMED
| NL595 | NL595_2_EOS_WL | TCFGADAMPOLPLARIDBUL_2_EOS_WL | PLARIDLAG |  |  | 14.8967 | 120.8186 | FTAP |  |  |  | BULACAN | Lagundi, Plaridel, Bulacan | PLARIDEL |  | CONFIRMED
| NL606 | NL606_700M+900MRRUChangeout_WL | TCFGAPOBLACIONNORZAGBUL_700M+900MRRUChangeout_WL | NORZAGTWN |  |  | 14.9106 | 121.0449 | FTAP |  |  |  | BULACAN | Cemetary Compound, Teodoro Gener St., Poblacion, Norzagaray, Bulacan | NORZAGARAY |  | NOT CONFIRMED
| NL606 | NL606_G9_WL_TRX Downgrade | TCFGAPOBLACIONNORZAGBUL_G9_WL_TRX Downgrade | NORZAGTWN |  |  | 14.9106 | 121.0449 | FTAP |  |  |  | BULACAN | Cemetary Compound, Teodoro Gener St., Poblacion, Norzagaray, Bulacan | NORZAGARAY |  | NOT CONFIRMED
| NL609 | NL609_1800MDismantling_WL | STAMARNTH_1800MDismantling_WL | STAMARNTH |  |  | 14.8775 | 121.0101 | FTAP |  |  |  | BULACAN | Lot 39, Lutgarda Building, Pulong Buhangin, Santa Maria, Bulacan | SANTA MARIA |  | CONFIRMED
| NL609 | NL609_1800MRRUMigration_WL | STAMARNTH_1800MRRUMigration_WL | STAMARNTH |  |  | 14.8775 | 121.0101 | FTAP |  |  |  | BULACAN | Lot 39, Lutgarda Building, Pulong Buhangin, Santa Maria, Bulacan | SANTA MARIA |  | CONFIRMED
| NL609 | NL609_700M+900MRRUChangeout_WL | STAMARNTH_700M+900MRRUChangeout_WL | STAMARNTH |  |  | 14.8775 | 121.0101 | FTAP |  |  |  | BULACAN | Lot 39, Lutgarda Building, Pulong Buhangin, Santa Maria, Bulacan | SANTA MARIA |  | CONFIRMED
| NL610 | NL610_2_EOS_WL | TCFGASAMPALOCCLUMPTBUL_2_EOS_WL | BLIWAGEST |  |  | 14.9805 | 120.9274 | FTAP |  |  |  | BULACAN | San Rafael Packaging Corporation, 157 Cagayan Valley Road, Sampaloc, San Rafael, Bulacan | SAN RAFAEL |  | NOT CONFIRMED
| NL610 | NL610_EOS_WL | TCFGASAMPALOCCLUMPTBUL_EOS_WL | BLIWAGEST |  |  | 14.9805 | 120.9274 | FTAP |  |  |  | BULACAN | San Rafael Packaging Corporation, 157 Cagayan Valley Road, Sampaloc, San Rafael, Bulacan | SAN RAFAEL |  | NOT CONFIRMED
| NL610 | NL610_G9_WL_TRX Downgrade | TCFGASAMPALOCCLUMPTBUL_G9_WL_TRX Downgrade | BLIWAGEST |  |  | 14.9805 | 120.9274 | FTAP |  |  |  | BULACAN | San Rafael Packaging Corporation, 157 Cagayan Valley Road, Sampaloc, San Rafael, Bulacan | SAN RAFAEL |  | NOT CONFIRMED
| NL611 | NL611_1800MDismantling_WL | BLIWAGSTH_1800MDismantling_WL | BLIWAGSTH |  |  | 14.9281 | 120.8934 | FTAP |  |  |  | BULACAN | Bonifacio Lopez St. (Tumana Road), Purok 5, Cambaog, Bustos, Bulacan | BUSTOS |  | NOT CONFIRMED
| NL611 | NL611_1800MRRUMigration_WL | BLIWAGSTH_1800MRRUMigration_WL | BLIWAGSTH |  |  | 14.9281 | 120.8934 | FTAP |  |  |  | BULACAN | Bonifacio Lopez St. (Tumana Road), Purok 5, Cambaog, Bustos, Bulacan | BUSTOS |  | NOT CONFIRMED
| NL612 | NL612_700M+900MRRUChangeout_WL | TCFGATAMBUBONGRAFAELBUL_700M+900MRRUChangeout_WL | SUBCBLUAG |  |  | 14.9712 | 120.9161 | FTAP |  |  |  | BULACAN | Ulingao, San Rafael, Bulacan | SAN RAFAEL |  | NOT CONFIRMED
| NL613 | NL613_EOS_WL | TCFGAPASOINTSIKRAFAELBUL_EOS_WL | SNRAFANTH |  |  | 15.001 | 120.9731 | FTAP |  |  |  | BULACAN | Pasong Intsik, San Rafael, Bulacan | SAN RAFAEL |  | NOT CONFIRMED
| NL613 | NL613_G9_WL_TRX Downgrade | TCFGAPASOINTSIKRAFAELBUL_G9_WL_TRX Downgrade | SNRAFANTH |  |  | 15.001 | 120.9731 | FTAP |  |  |  | BULACAN | Pasong Intsik, San Rafael, Bulacan | SAN RAFAEL |  | NOT CONFIRMED
| NL617 | NL617_1800MDismantling_WL | BIAKNBTO_1800MDismantling_WL | BIAKNBTO |  |  | 15.1078 | 121.0623 | FTAP |  |  |  | BULACAN | Sitio Muzon, Buhol na Mangga, San Ildefonso, Bulacan | SAN ILDELFONSO |  | NOT CONFIRMED
| NL617 | NL617_EOS_WL | BIAKNBTO_EOS_WL | BIAKNBTO |  |  | 15.1078 | 121.0623 | FTAP |  |  |  | BULACAN | Sitio Muzon, Buhol na Mangga, San Ildefonso, Bulacan | SAN ILDELFONSO |  | NOT CONFIRMED
| NL622 | NL622_700M+900MRRUChangeout_WL | HAGONOEST_700M+900MRRUChangeout_WL | HAGONOEST |  |  | 14.8694 | 120.7644 | FTAP |  |  |  | BULACAN | Iba, Hagonoy, Bulacan | HAGONOY |  | NOT CONFIRMED
| NL626 | NL626_EOS_WL | TCFGASAPANGPUTIKSILDEFBUL_EOS_WL | SAPAPUTIK |  |  | 15.0358 | 120.9628 | FTAP |  |  |  | BULACAN | Sapang Putik, San Ildefonso, Bulacan | SAN ILDELFONSO |  | NOT CONFIRMED
| NL628 | NL628_1800M+2100MRRUChangeout_WL | TCFGAAKLESILDEFBUL_1800M+2100MRRUChangeout_WL | AKLEFONSO |  |  | 15.0501 | 121.062 | FTAP |  |  |  | BULACAN | Sitio Gulod, Akle, San Ildefonso, Bulacan | SAN ILDELFONSO |  | NOT CONFIRMED
| NL628 | NL628_700M+900MRRUChangeout_WL | TCFGAAKLESILDEFBUL_700M+900MRRUChangeout_WL | AKLEFONSO |  |  | 15.0501 | 121.062 | FTAP |  |  |  | BULACAN | Sitio Gulod, Akle, San Ildefonso, Bulacan | SAN ILDELFONSO |  | NOT CONFIRMED
| NL628 | NL628_G9G18_WL_TRX Downgrade | TCFGAAKLESILDEFBUL_G9G18_WL_TRX Downgrade | AKLEFONSO |  |  | 15.0501 | 121.062 | FTAP |  |  |  | BULACAN | Sitio Gulod, Akle, San Ildefonso, Bulacan | SAN ILDELFONSO |  | NOT CONFIRMED
| NL2807 | NL2807_NR26_64T64R_WL | BULACSMARIABUL_NR26_64T64R_WL | BULACSMARIABUL |  |  | 14.8395 | 121.0246 |  |  |  |  | BULACAN | Sitio Paigkas, Bulac, SANTA MARIA, BULACAN, REGION III (CENTRAL LUZON), NL | SANTA MARIA
| NL2781 | NL2781_NR26_4T4R_WL | TCCRELOURDESSUBDPLARIDBUL_NR26_4T4R_WL | TCCRELOURDESSUBDPLARIDBUL |  |  | 14.8718 | 120.861 |  |  |  |  | BULACAN | Sipat, PLARIDEL, BULACAN, REGION III (CENTRAL LUZON), NL | PLARIDEL
| NL544 | NL544_NR26_64T64R_WL | TABANGPLARIDBUL_NR26_64T64R_WL | PLARIDEL |  |  | 14.8826 | 120.8612 |  |  |  |  | BULACAN | Tabang, Plaridel, Bulacan | PLARIDEL
| NL2777 | NL2777_NR35_WL | TCCREPRENZA1MRILAOBUL_NR35_WL | TCCREPRENZA1MRILAOBUL |  |  | 14.789 | 120.9763 |  |  |  |  | BULACAN | Santa Rosa II, MARILAO, BULACAN, REGION III (CENTRAL LUZON), NL | MARILAO
| NL5389 | NL5389_NR26_64T64R_WL_add sector | TCAICLOMADEGATO3MRILAOBUL_NR26_64T64R_WL_add sector | LOMADEGATO3MRILAOBUL |  |  | 14.7844 | 121.0114 |  |  |  |  | BULACAN | Loma de Gato, MARILAO, BULACAN, REGION III (CENTRAL LUZON), NL | MARILAO
| NL2077 | NL2077_NR26_64T64R_40M_WL | TCMCRMOJONMLOLOSBUL_NR26_64T64R_40M_WL | MOJONBUL |  |  | 14.8652 | 120.8311 |  |  |  |  | BULACAN | Shok St. Barangay Sumapa, Lugam, Malolos, Bulacan | MALOLOS CITY (CAPITAL)
| NL315 | NL315_NR26_64T64R_40M_WL | TCFGAPINAGBAKAHANMLOLOSBUL_NR26_64T64R_40M_WL | LOOKFIRST |  |  | 14.8757 | 120.818 |  |  |  |  | BULACAN | Bulacan Garden, Gardenville Subd., Pinagbakahan, Malolos, Bulacan | MALOLOS CITY (CAPITAL)
| NL545 | NL545_NR26_64T64R_40M_WL | TCMCRSUMAPANGMTANDAMLOLOSBUL_NR26_64T64R_40M_WL | MALOLOS2 |  |  | 14.8537 | 120.8194 | MIDC |  |  |  | BULACAN | Sumapang Matanda, Malolos, Bulacan | MALOLOS CITY (CAPITAL)
| NL594 | NL594_NR26_64T64R_40M_WL | TCFGABALITEMLOLOSBUL_NR26_64T64R_40M_WL | MATIMBMAL |  |  | 14.822 | 120.8361 |  |  |  |  | BULACAN | 411 (Fisheries School), Balite, Malolos, Bulacan | MALOLOS CITY (CAPITAL)
| NL1522 | NL1522_EOS_WL | TCFGAHERITAGEMEYCAUBUL_EOS_WL | HERITAGEMEY |  |  | 14.7644 | 121.0118 | FTAP |  |  |  | BULACAN | Lot #138, Fabre St., Bahay Pare, Meycauayan, Bulacan | MEYCAUAYAN CITY
| NL2230 | NL2230_1800MDismantling_WL | PH6ARENAID_1800MDismantling_WL | PH6ARENAID |  |  | 14.7935 | 120.9535 |  |  |  |  | BULACAN | Philippine Arena, Ciudad de Victoria, Bolacan, Bocaue, Bulacan | BOCAUE
| NL2782 | NL2782_L700_WL | TCATCSANJOSEPLARIDBUL_L700_WL | TCATCSANJOSEPLARIDBUL |  |  | 14.9056 | 120.8961 |  |  |  |  | BULACAN | San Jose, PLARIDEL, BULACAN, REGION III (CENTRAL LUZON), NL | PLARIDEL
| NL2782 | NL2782_L900_WL | TCATCSANJOSEPLARIDBUL_L900_WL | TCATCSANJOSEPLARIDBUL |  |  | 14.9056 | 120.8961 |  |  |  |  | BULACAN | San Jose, PLARIDEL, BULACAN, REGION III (CENTRAL LUZON), NL | PLARIDEL
| NL545 | NL545_EOS_WL | TCMCRSUMAPANGMTANDAMLOLOSBUL_EOS_WL | MALOLOS2 |  |  | 14.8537 | 120.8194 | MIDC |  |  |  | BULACAN | Sumapang Matanda, Malolos, Bulacan | MALOLOS CITY (CAPITAL)
| NL545 | NL545_G9_WL_TRX Downgrade | TCMCRSUMAPANGMTANDAMLOLOSBUL_G9_WL_TRX Downgrade | MALOLOS2 |  |  | 14.8537 | 120.8194 | MIDC |  |  |  | BULACAN | Sumapang Matanda, Malolos, Bulacan | MALOLOS CITY (CAPITAL)
| NL570 | NL570_EOS_WL | TCFGAPEREZMEYCAUBUL_EOS_WL | PEREZMEY |  |  | 14.7577 | 120.9929 | FTAP |  |  |  | BULACAN | Perez St., Perez, Meycauayan, Bulacan | MEYCAUAYAN CITY
| NL573 | NL573_700M+900MRRUChangeout_WL | LOMADEGATO1MRILAOBUL_700M+900MRRUChangeout_WL | LOMADEGATO1MRILAOBUL |  |  | 14.78 | 121.0214 | FTAP |  |  |  | BULACAN | PH4 Heritage Homes Subd., Mars St., Loma de Gato, Marilao, Bulacan | MARILAO
| NL580 | NL580_EOS_WL | TCFGASANVICENTESMARIABUL_EOS_WL | STAMAREAST |  |  | 14.8075 | 121.0014 | FTAP |  |  |  | BULACAN | Lot 230, Gov. F. Halili Ave., San Vicente, Santa Maria, Bulacan | SANTA MARIA
| NL595 | NL595_2_EOS_WL | TCFGADAMPOLPLARIDBUL_2_EOS_WL | PLARIDLAG |  |  | 14.8967 | 120.8186 | FTAP |  |  |  | BULACAN | Lagundi, Plaridel, Bulacan | PLARIDEL
| NL595 | NL595_EOS_WL | TCFGADAMPOLPLARIDBUL_EOS_WL | PLARIDLAG |  |  | 14.8967 | 120.8186 | FTAP |  |  |  | BULACAN | Lagundi, Plaridel, Bulacan | PLARIDEL
| NL595 | NL595_G9G18_WL_TRX Downgrade | TCFGADAMPOLPLARIDBUL_G9G18_WL_TRX Downgrade | PLARIDLAG |  |  | 14.8967 | 120.8186 | FTAP |  |  |  | BULACAN | Lagundi, Plaridel, Bulacan | PLARIDEL
| NL1023 | NL1023_EOS_WL | TCFGALAWAMEYCAUBUL_EOS_WL | LAWAMEYC |  |  | 14.7297 | 120.9706 | FTAP |  |  |  | BULACAN | Caingin Road, Lawa, Meycauayan, Bulacan | MEYCAUAYAN CITY | CRISTIAN INOCENCIO | CONFIRMED | With PO | 28/11/2025 | 14/01/2026 | HARDWARE APPROVED - Jan 22, 2026 L1 CLOSED - Feb 3, 2026 |  | APPROVED | NOV 28, 2025 (DAY 1) MOS/PRE INSTALL - MAY LACKING MATERIAL JAN 14, 2026 (DAY 2) INTEGRATION/INSTALLATION JAN 15, 2026 (DAY 3) DISMANTLING JAN 16, 2026 (DAY 4) ISDPQC - BETWEEN 10:30-11:30 NA NAGREPLY ANG FO PARA SA LOG IN. DI NAKAPASOK SA SITE KASI YUNG FO NAGSABI NA IPULLOUT MUNA ANG DISMANTLED MATERIALS AT IDALA SA STA MARIA GLOBE HUB BEFORE SILA MAKAPAGPROCEED SA ACTIVITY. 12PM SILA NAKAALIS THEN NAKABALIK SILA SA SITE AROUND 4PM NA. ANG FO DI NA NAMAN NAGREPLY AGAD KAYA INABOT NA SILA NG 5PM. JAN 21, 2026 (DAY 5) ALARM CLEARING/ISDPQC (JAN 19, 2026 NAG ALARM ANG SITE) - Halos buong araw sila nag alarm Clearing. JAN 22, 2026 (DAY 6) ISDPQC - HARDWARE APPROVED
| NL1380 | NL1380_EOS_WL | TCMCRSANTONINOPLARIDBUL_EOS_WL | STONINO |  |  | 14.88 | 120.8367 | MIDC |  |  |  | BULACAN | Bulihan, Plaridel, Bulacan | PLARIDEL | CRISTIAN INOCENCIO | CONFIRMED | With PO | 29/11/2025 | 2025-01-12 | HARDWARE APPROVED - 12.04.25 L1 APPROVED - 12.11.25 |  | APPROVED | PAT (GWE & EOS - NO PAT)
| NL1522 | NL1522_EOS_WL | TCFGAHERITAGEMEYCAUBUL_EOS_WL | HERITAGEMEY |  |  | 14.7644 | 121.0118 | FTAP |  |  |  | BULACAN | Lot #138, Fabre St., Bahay Pare, Meycauayan, Bulacan | MEYCAUAYAN CITY | CRISTIAN INOCENCIO | CONFIRMED | With PO | 29/11/2025 | 2025-05-12 | HARDWARE APPROVED - JAN 17, 2026 L1 APPROVED - |  | WAITING FOR APPROVAL | NOV 29, 2025 (1) MOS ONLY Dahil nag integration/install sila agad sa NL1023 DEC 5, 2025 (2) PRE INSTALLATION DEC 13, 2025 (3) ALARM CLEARING - DI NACLEAR ANG ALARM. NAGREQUEST PA NG JUMPER CABLE PARA MAILIPAT SA IBANG LOCATION ANG RRU DEC 17, 2025 (4) ALARM CLEARING - NAGTRY PARIN MAG CLEAR NG ALARM ANG TEAM WHILE WAITING SA JUMPER CABLE. DI MAREACH ANG HT, KAHIT ILANG BESES NA NAGFOLLOW UP SA JUMPER CABLE NA REQUEST. 7PM NA DUMATING. DEC 18, 2025 (5) ALARM CLEARING DONE DEC 20, 2025 (6) DISMANTLING - 2:07PM BAD WEATHER NA NG TULOY TULOY JAN 12, 2026 (7) ISDPQC - HINDI NAKAPASOK NG SITE DUE TO ROC LOG IN NA NEED BEFORE MAGSTART SA ACTIVITY, WALA NI ISA SA CONTACT NG NOC ANG SUMASAGOT. NAGPATULONG DIN KAMI SA HT PERO KAHIT SILA DI RIN SUMASAGOT AT MAHIRAP I-REACH. 4PM NAGREPLY ANG NOC ABOUT SA LOG IN PERO NAKA DAY OFF DAW, NAGPATULONG SI CRISTIAN SA LOG IN PERO DI NA SUMAGOT JAN 13, 2026 (8) ISDPQC - RECTIFICATION/ISDPQC JAN 15, 2026 (9) HARDWARE APPROVED JAN 23, 2026 (10) SV DONE
| NL1989 | NL1989_EOS_WL | TCMCRMHBANGPARANGSMARIABUL_EOS_WL | MPARANGBUL |  |  | 14.7938 | 120.9602 | MIDC |  |  |  | BULACAN | J.P. Rizal Street,, Mahabang Parang, Santa Maria, Bulacan | SANTA MARIA | CRISTIAN INOCENCIO | CONFIRMED | With PO | 2025-10-12 | 15/12/2025 | HARDWARE APPROVED - FEB 12, 2026 L1 APPROVED - FEB 16, 2026 |  | APPROVED | DEc 16, 2025 - Pre installation Done FEB 10, 2026 (2) INSTALLATION; INTEGRATION, ISDPQC FEB 11, 2026 (3) ALARM CLEARING; ISDPQC PHOTO TAKING; DISMANTLING FEB 12, 2026 (4) HARDWARE APPROVED; SITE VERIFIED
| NL545 | NL545_EOS_WL | TCMCRSUMAPANGMTANDAMLOLOSBUL_EOS_WL | MALOLOS2 |  |  | 14.8537 | 120.8194 | MIDC |  |  |  | BULACAN | Sumapang Matanda, Malolos, Bulacan | MALOLOS CITY (CAPITAL) |  | CONFIRMED | With PO |  |  |  |  | APPROVED
| NL568 | NL568_EOS_WL | MEYCEAST_EOS_WL | MEYCEAST |  |  | 14.7746 | 121.0031 | MIDC |  |  |  | BULACAN | De Guzman Cmpd, Pajo, Meycauayan, Bulacan | MEYCAUAYAN CITY | CRISTIAN INOCENCIO | CONFIRMED | With PO | 2025-09-12 | 2025-12-12 | HARDWARE APPROVED - L1 APPROVED - |  | APPROVED | Pre-install done DEC 9, 2025 (1) MOS ONLY, KASABAY ANG NL570 AT NL1522 DECEMBER 10, 2025 (2) PRE-INSTALLATION - DI NAKAPAG PROCEED SA ACTIVITY DAHIL AYAW PAYAGAN ANG TEAM SA LOG IN DAHIL MAY ALARM PA SA NL1522 NA NEED ICLOSE(ANG PROBLEMA, DI NAMAN PWEDE I-CLEAR ANG ALARM DAHIL MAY NEED PANG MATERIALS) DEC 12, 2025 (3) PRE-INSTALL DECEMBER 19, 2025 (4) INSTALLATION & INTEGRATION JAN 17, 2026 (5) DISMANTLING JAN 24, 2026 (6) DI NAKAPAG PROCEED SA ACTIVITY DAHIL NAREJECT ANG EHS SA ISDP DAHIL ANG FIRE EXTINGUISHER AY MAY MOIST SA GAUGE. AYAW IACCEPT NG GSC/CHECKER. TRINY PAKIUSAPAN PERO AYAW TALAGA PUMAYAG. FEB 3, 2026 (7) HAPON NA NAKARATING ANG TEAM SA SITE DAHIL DINAANAN PA NILA ANG NL1023 PARA MAL1 CLOSED NA. PAGDATING NILA SA NL568, NATAGALAN NA NAMAN SILA MAG PROCEED NG ACTIVITY DAHIL HALOS AYAW NA NAMAN MAGPAPROCEED NG FO SA ACTIVITY DAHIL PINUPUSH ANG PULLOUT NG DISMANTLED MATERIALS FEB 4, 2026 (8) HINDI PINAPAPROCEED NI FO ANG TEAM SA ACTIVITY. PINAPAPULL OUT NI FO ANG DISMANTLED MATERIALS. FEB 7, 2026 (9) 100% UPLOADED PHOTOS; UPON CHECKING OF GSC, LACKING PA NG OUTDOOR LABELS AND MAY KONTI PANG NEED IRECTIFY.
| NL570 | NL570_EOS_WL | TCFGAPEREZMEYCAUBUL_EOS_WL | PEREZMEY |  |  | 14.7577 | 120.9929 | FTAP |  |  |  | BULACAN | Perez St., Perez, Meycauayan, Bulacan | MEYCAUAYAN CITY | CRISTIAN INOCENCIO | CONFIRMED | With PO | 2025-09-12 | 23/01/2026 | HARDWARE APPROVED - L1 APPROVED - |  | WAITING FOR APPROVAL | Dec 16, 2025 - Pre install Jan 23, 2026 - Installation Jan 24, 2026 - Integration, but around 10:52am Mam MJ announced to the GC that it is already DEFERRED DUE TO SHORT JUMPER CABLE Followed up many times but still NO JUMPER yet Feb 12, 2026 - Sir Leo said that there is no Inventory yet for this site and they will work it out
| NL573 | NL573_700M+900MRRUChangeout_WL | LOMADEGATO1MRILAOBUL_700M+900MRRUChangeout_WL | LOMADEGATO1MRILAOBUL |  |  | 14.78 | 121.0214 | FTAP |  |  |  | BULACAN | PH4 Heritage Homes Subd., Mars St., Loma de Gato, Marilao, Bulacan | MARILAO |  | CONFIRMED | [5 empty] | APPROVED
| NL580 | NL580_EOS_WL | TCFGASANVICENTESMARIABUL_EOS_WL | STAMAREAST |  |  | 14.8075 | 121.0014 | FTAP |  |  |  | BULACAN | Lot 230, Gov. F. Halili Ave., San Vicente, Santa Maria, Bulacan | SANTA MARIA |  | CONFIRMED | [5 empty] | APPROVED
| NL595 | NL595_EOS_WL | TCFGADAMPOLPLARIDBUL_EOS_WL | PLARIDLAG |  |  | 14.8967 | 120.8186 | FTAP |  |  |  | BULACAN | Lagundi, Plaridel, Bulacan | PLARIDEL |  | CONFIRMED | [5 empty] | APPROVED
| NL595 | NL595_G9G18_WL_TRX Downgrade | TCFGADAMPOLPLARIDBUL_G9G18_WL_TRX Downgrade | PLARIDLAG |  |  | 14.8967 | 120.8186 | FTAP |  |  |  | BULACAN | Lagundi, Plaridel, Bulacan | PLARIDEL |  | CONFIRMED | [5 empty] | APPROVED
DISMANTLING | NL101 | NL101_BBPDismantling_WL | TCFGAPRK7DILADILASTRITAPAM_BBPDismantling_WL | EOSEUL-RRU25-1805 |  |  | 15.0286 | 120.5696 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Purok 7, Dila-dila, Santa Rita, Pampanga | SANTA RITA | LEMUEL NILL MALTO
CHANGEOUT | NL101 | NL101_BBU+UMPTChangeout_WL | TCFGAPRK7DILADILASTRITAPAM_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1481 |  |  | 15.0286 | 120.5696 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Purok 7, Dila-dila, Santa Rita, Pampanga | SANTA RITA | LEMUEL NILL MALTO
DISMANTLING | NL1020 | NL1020_BBPDismantling_WL | LEISURBAK_BBPDismantling_WL | EOSEUL-RRU25-1747 |  |  | 15.1846 | 120.5092 | GT BAU |  |  |  | PAMPANGA | FM Hill transmitter, Sapangbato, Angeles City, Pampanga | ANGELES CITY
DISMANTLING/MIGRATION | NL1020 | NL1020_BBUDismantling+Migration_WL | LEISURBAK_BBUDismantling+Migration_WL | EOSEUL-RRU25-1171 |  |  | 15.1846 | 120.5092 | GT BAU |  |  |  | PAMPANGA | FM Hill transmitter, Sapangbato, Angeles City, Pampanga | ANGELES CITY
DISMANTLING | NL103 | NL103_BBPDismantling_WL | TCFGALOURDESMINALINPAM_BBPDismantling_WL | EOSEUL-RRU25-1658 |  |  | 14.9588 | 120.731 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Lourdes, Minalin, Pampanga | MINALIN | LEMUEL NILL MALTO
DISMANTLING | NL105 | NL105_BBPDismantling_WL | TCFGASANISIDROLUBAPPAM_BBPDismantling_WL | EOSEUL-RRU25-2057 |  |  | 14.8856 | 120.5189 | FTAP |  |  |  | PAMPANGA | San Isidro, Lubao, Pampanga | LUBAO
CHANGEOUT | NL106 | NL106_700M+900MRRUChangeout_WL | VILLASOL_700M+900MRRUChangeout_WL | VILLASOL |  |  | 15.1663 | 120.5633 | FTAP | APPLIED | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Along Don Juico Ave., beside Oasis Hotel, Malabanias, Angeles City, Pampanga | ANGELES CITY | EDGAR AQUINO / LEMUEL NILL MALTO
DISMANTLING | NL106 | NL106_BBPDismantling_WL | VILLASOL_BBPDismantling_WL | EOSEUL-RRU25-1825 |  |  | 15.1663 | 120.5633 | FTAP | APPLIED | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Along Don Juico Ave., beside Oasis Hotel, Malabanias, Angeles City, Pampanga | ANGELES CITY | EDGAR AQUINO / LEMUEL NILL MALTO
DISMANTLING/MIGRATION | NL106 | NL106_BBUDismantling+Migration_WL | VILLASOL_BBUDismantling+Migration_WL | EOSEUL-RRU25-1625 |  |  | 15.1663 | 120.5633 | FTAP | APPLIED | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Along Don Juico Ave., beside Oasis Hotel, Malabanias, Angeles City, Pampanga | ANGELES CITY | EDGAR AQUINO / LEMUEL NILL MALTO
DISMANTLING | NL108 | NL108_BBPDismantling_WL | LUCIAMAG_BBPDismantling_WL | EOSEUL-RRU25-1750 |  |  | 15.2267 | 120.6323 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Sta. Lucia Resettlement, San Isidro, Magalang, Pampanga | MAGALANG | EDGAR AQUINO / LEMUEL NILL MALTO
DISMANTLING | NL110 | NL110_BBPDismantling_WL | TCFGAMAPANIQUICNDABAPAM_BBPDismantling_WL | EOSEUL-RRU25-1801 |  |  | 15.106 | 120.9216 | FTAP |  |  |  | PAMPANGA | Mapaniqui, Candaba, Pampanga | CANDABA
DISMANTLING/MIGRATION | NL110 | NL110_BBUDismantling+Migration_WL | TCFGAMAPANIQUICNDABAPAM_BBUDismantling+Migration_WL | EOSEUL-RRU25-1462 |  |  | 15.106 | 120.9216 | FTAP |  |  |  | PAMPANGA | Mapaniqui, Candaba, Pampanga | CANDABA
EOS | NL110 | NL110_EOS_WL | TCFGAMAPANIQUICNDABAPAM_EOS_WL | PNIQUIPAM |  |  | 15.106 | 120.9216 | FTAP |  |  |  | PAMPANGA | Mapaniqui, Candaba, Pampanga | CANDABA
DOWNGRADE | NL110 | NL110_G9_WL_TRX Downgrade | TCFGAMAPANIQUICNDABAPAM_G9_WL_TRX Downgrade | PNIQUIPAM |  |  | 15.106 | 120.9216 | FTAP |  |  |  | PAMPANGA | Mapaniqui, Candaba, Pampanga | CANDABA
DISMANTLING | NL111 | NL111_BBPDismantling_WL | TCFGATAGULODCNDABAPAM_BBPDismantling_WL | EOSEUL-RRU25-1660 |  |  | 15.2074 | 120.9145 | FTAP |  |  |  | PAMPANGA | #165 Centro 2, Tagulod, Candaba, Pampanga | CANDABA
EOS | NL111 | NL111_EOS_WL | TCFGATAGULODCNDABAPAM_EOS_WL | TGULODPAM |  |  | 15.2074 | 120.9145 | FTAP |  |  |  | PAMPANGA | #165 Centro 2, Tagulod, Candaba, Pampanga | CANDABA
DOWNGRADE | NL111 | NL111_G9_WL_TRX Downgrade | TCFGATAGULODCNDABAPAM_G9_WL_TRX Downgrade | TGULODPAM |  |  | 15.2074 | 120.9145 | FTAP |  |  |  | PAMPANGA | #165 Centro 2, Tagulod, Candaba, Pampanga | CANDABA
EOS | NL112 | NL112_EOS_WL | TCFGAMAGUMBALICNDABAPAM_EOS_WL | SALAPAM |  |  | 15.135 | 120.9073 | FTAP |  |  |  | PAMPANGA | Magumbali, Candaba, Pampanga | CANDABA
EOS | NL113 | NL113_EOS_WL | MAGALAEST_EOS_WL | MAGALAEST |  |  | 15.2263 | 120.6863 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | San Agustin, Magalang, Pampanga | MAGALANG | EDGAR AQUINO / LEMUEL NILL MALTO
DISMANTLING | NL114 | NL114_BBPDismantling_WL | STATERESA_BBPDismantling_WL | EOSEUL-RRU25-1791 |  |  | 14.8918 | 120.5547 | FTAP |  |  |  | PAMPANGA | Purok 4, Calangain, Lubao, Pampanga | LUBAO
CHANGEOUT | NL114 | NL114_BBU+UMPTChangeout_WL | STATERESA_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1365 |  |  | 14.8918 | 120.5547 | FTAP |  |  |  | PAMPANGA | Purok 4, Calangain, Lubao, Pampanga | LUBAO
DISMANTLING | NL115 | NL115_BBPDismantling_WL | TCFGASTATERESA1STLUBAPPAM_BBPDismantling_WL | EOSEUL-RRU25-1813 |  |  | 14.9266 | 120.5618 | FTAP |  |  |  | PAMPANGA | Purok 1, Santa Teresa 1st, Lubao, Pampanga | LUBAO
CHANGEOUT | NL1168 | NL1168_1800M+2100MRRUChangeout_WL | DELROSAR_1800M+2100MRRUChangeout_WL | DELROSAR |  |  | 15.0732 | 120.6444 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Gold Mine Hardware, San Agustin, San Fernando, Pampanga | CITY OF SAN FERNANDO | LEMUEL NILL MALTO
DISMANTLING/MIGRATION | NL1168 | NL1168_1800MRRUDismantling+Migration_WL | DELROSAR_1800MRRUDismantling+Migration_WL | EOSEUL-RRU25-0281 |  |  | 15.0732 | 120.6444 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Gold Mine Hardware, San Agustin, San Fernando, Pampanga | CITY OF SAN FERNANDO | LEMUEL NILL MALTO
DISMANTLING | NL1168 | NL1168_2100MDismantling_WL | DELROSAR_2100MDismantling_WL | DELROSAR |  |  | 15.0732 | 120.6444 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Gold Mine Hardware, San Agustin, San Fernando, Pampanga | CITY OF SAN FERNANDO | LEMUEL NILL MALTO
CHANGEOUT | NL1168 | NL1168_700M+900MRRUChangeout_WL | DELROSAR_700M+900MRRUChangeout_WL | DELROSAR |  |  | 15.0732 | 120.6444 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Gold Mine Hardware, San Agustin, San Fernando, Pampanga | CITY OF SAN FERNANDO | LEMUEL NILL MALTO
DOWNGRADE | NL1168 | NL1168_G18_WL_TRX Downgrade | DELROSAR_G18_WL_TRX Downgrade | DELROSAR |  |  | 15.0732 | 120.6444 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Gold Mine Hardware, San Agustin, San Fernando, Pampanga | CITY OF SAN FERNANDO | LEMUEL NILL MALTO
DISMANTLING | NL1171 | NL1171_2100MDismantling_WL | SNJUANP_2100MDismantling_WL | SNJUANP |  |  | 15.0242 | 120.6768 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Santo Niño, San Fernando, Pampanga | CITY OF SAN FERNANDO | LEMUEL NILL MALTO
DISMANTLING | NL118 | NL118_BBPDismantling_WL | ANGELESIP_BBPDismantling_WL | EOSEUL-RRU25-1710 |  |  | 15.1171 | 120.6027 | FTAP | APPLIED |  |  | PAMPANGA | Angeles Industrial Park, Telabastagan, San Fernando, Pampanga | ANGELES CITY | EDGAR AQUINO / LEMUEL NILL MALTO
CHANGEOUT | NL118 | NL118_BBU+UMPTChangeout_WL | ANGELESIP_BBU+UMPTChangeout_WL | EOSEUL-RRU25-0949 |  |  | 15.1171 | 120.6027 | FTAP | APPLIED |  |  | PAMPANGA | Angeles Industrial Park, Telabastagan, San Fernando, Pampanga | ANGELES CITY | EDGAR AQUINO / LEMUEL NILL MALTO
EOS | NL118 | NL118_EOS_WL | TCFGAANGELESIPBCOLORPAM_EOS_WL | ANGELESIP |  |  | 15.1171 | 120.6027 | FTAP | APPLIED |  |  | PAMPANGA | Angeles Industrial Park, Telabastagan, San Fernando, Pampanga | ANGELES CITY | EDGAR AQUINO / LEMUEL NILL MALTO
CHANGEOUT | NL1187 | NL1187_BBU+UMPTChangeout_WL | ANGELEAST_BBU+UMPTChangeout_WL | EOSEUL-RRU25-0948 |  |  | 15.1477 | 120.6107 | MIDC |  |  |  | PAMPANGA | Tabun, Angeles City, Pampanga | ANGELES CITY
DISMANTLING | NL1191 | NL1191_BBPDismantling_WL | TCMCRBALITISFERNPAM_BBPDismantling_WL | EOSEUL-RRU25-1662 |  |  | 15.1025 | 120.6256 | MIDC |  |  |  | PAMPANGA | near Cca Cola McArthur, Baliti, San Fernando, Pampanga | ANGELES CITY
DISMANTLING | NL1192 | NL1192_BBPDismantling_WL | CASINOPAM_BBPDismantling_WL | EOSEUL-RRU25-1866 |  |  | 15.1639 | 120.5897 | GT BAU |  |  |  | PAMPANGA | Casino Filipino Angeles, Balibago, Angeles City, Pampanga | ANGELES CITY
DISMANTLING/MIGRATION | NL1195 | NL1195_BBUDismantling+Migration_WL | TCFGASAGUINSFERNPAM_BBUDismantling+Migration_WL | EOSEUL-RRU25-1488 |  |  | 15.0873 | 120.6228 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Purok 7, Saguin, San Fernando, Pampanga | CITY OF SAN FERNANDO | LEMUEL NILL MALTO
EOS | NL1195 | NL1195_EOS_WL | TCFGASAGUINSFERNPAM_EOS_WL | DLAPAZPAM |  |  | 15.0873 | 120.6228 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Purok 7, Saguin, San Fernando, Pampanga | CITY OF SAN FERNANDO | LEMUEL NILL MALTO
DISMANTLING | NL125 | NL125_BBPDismantling_WL | CLARK2_BBPDismantling_WL | EOSEUL-RRU25-1872 |  |  | 15.1924 | 120.5322 | GT BAU |  |  |  | PAMPANGA | Lily Hill, Clarkfield Airfield, Sapangbato, Angeles City, Pampanga | ANGELES CITY
DISMANTLING | NL126 | NL126_BBPDismantling_WL | CLRKECO_BBPDismantling_WL | EOSEUL-RRU25-1665 |  |  | 15.1783 | 120.5181 | GT BAU |  |  |  | PAMPANGA | CDC Tower, CP Garcia cor. CP Reymundo,Clark Special Eco Zone, Sapangbato, Angeles City, Pampanga | ANGELES CITY
DISMANTLING | NL127 | NL127_BBPDismantling_WL | TCMCRCAMACHILESMBLCATPAM_BBPDismantling_WL | EOSEUL-RRU25-1666 |  |  | 15.1914 | 120.5809 | MIDC |  |  |  | PAMPANGA | Garcia Lot, Camachiles, Mabalacat, Pampanga | MABALACAT CITY
DISMANTLING/MIGRATION | NL128 | NL128_1800MRRUDismantling+Migration_WL | DAU2_1800MRRUDismantling+Migration_WL | EOSEUL-RRU25-0296 |  |  | 15.1768 | 120.6029 | GT BAU |  |  |  | PAMPANGA | Dau Homesite, 6091 Lansones St., Duquit, Mabalacat, Pampanga | MABALACAT CITY
DISMANTLING | NL128 | NL128_BBPDismantling_WL | DAU2_BBPDismantling_WL | EOSEUL-RRU25-1667 |  |  | 15.1768 | 120.6029 | GT BAU |  |  |  | PAMPANGA | Dau Homesite, 6091 Lansones St., Duquit, Mabalacat, Pampanga | MABALACAT CITY
EOS | NL128 | NL128_EOS_WL | DAU2_EOS_WL | DAU2 |  |  | 15.1768 | 120.6029 | GT BAU |  |  |  | PAMPANGA | Dau Homesite, 6091 Lansones St., Duquit, Mabalacat, Pampanga | MABALACAT CITY
DOWNGRADE | NL128 | NL128_G18_WL_TRX Downgrade | DAU2_G18_WL_TRX Downgrade | EOSEUL-RRU25-0741 |  |  | 15.1768 | 120.6029 | GT BAU |  |  |  | PAMPANGA | Dau Homesite, 6091 Lansones St., Duquit, Mabalacat, Pampanga | MABALACAT CITY
CHANGEOUT | NL128 | NL128_UMPTChangeOut_WL | DAU2_UMPTChangeOut_WL | EOSEUL-RRU25-1068 |  |  | 15.1768 | 120.6029 | GT BAU |  |  |  | PAMPANGA | Dau Homesite, 6091 Lansones St., Duquit, Mabalacat, Pampanga | MABALACAT CITY
CHANGEOUT | NL129 | NL129_BBU+UMPTChangeout_WL | DAU3_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1069 |  |  | 15.1988 | 120.5992 | MIDC |  |  |  | PAMPANGA | Sapang Biabas, Mabalacat, Pampanga | MABALACAT CITY
EOS | NL129 | NL129_EOS_WL | TCMCRSPANGBIABASMBLCATPAM_EOS_WL | DAU3 |  |  | 15.1988 | 120.5992 | MIDC |  |  |  | PAMPANGA | Sapang Biabas, Mabalacat, Pampanga | MABALACAT CITY
DISMANTLING | NL130 | NL130_BBPDismantling_WL | TCFGAVALDEZFLORIDPAM_BBPDismantling_WL | EOSEUL-RRU25-1668 |  |  | 14.9864 | 120.54 | FTAP |  |  |  | PAMPANGA | Valdez, Floridablanca, Pampanga | FLORIDABLANCA
CHANGEOUT | NL130 | NL130_BBU+UMPTChangeout_WL | TCFGAVALDEZFLORIDPAM_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1522 |  |  | 14.9864 | 120.54 | FTAP |  |  |  | PAMPANGA | Valdez, Floridablanca, Pampanga | FLORIDABLANCA
DISMANTLING/MIGRATION | NL131 | NL131_BBUDismantling+Migration_WL | FLORIDABL_BBUDismantling+Migration_WL | EOSEUL-RRU25-1094 |  |  | 14.981 | 120.5138 | MIDC |  |  |  | PAMPANGA | Phase 3, Fortuna, Floridablanca, Pampanga | FLORIDABLANCA
EOS | NL133 | NL133_1_EOS_WL | TCMCRSNNICOLAS1GUAGUAPAM_1_EOS_WL | GUAGUA |  |  | 14.9689 | 120.6347 | MIDC |  |  |  | PAMPANGA | San Nicolas 1st, Guagua, Pampanga | GUAGUA
DISMANTLING | NL133 | NL133_2100MDismantling_WL | TCMCRSNNICOLAS1GUAGUAPAM_2100MDismantling_WL | GUAGUA |  |  | 14.9689 | 120.6347 | MIDC |  |  |  | PAMPANGA | San Nicolas 1st, Guagua, Pampanga | GUAGUA
EOS | NL133 | NL133_EOS_WL | TCMCRSNNICOLAS1GUAGUAPAM_EOS_WL | GUAGUA |  |  | 14.9689 | 120.6347 | MIDC |  |  |  | PAMPANGA | San Nicolas 1st, Guagua, Pampanga | GUAGUA
DOWNGRADE | NL133 | NL133_G9_WL_TRX Downgrade | TCMCRSNNICOLAS1GUAGUAPAM_G9_WL_TRX Downgrade | GUAGUA |  |  | 14.9689 | 120.6347 | MIDC |  |  |  | PAMPANGA | San Nicolas 1st, Guagua, Pampanga | GUAGUA
DISMANTLING | NL134 | NL134_BBPDismantling_WL | GUTADPAM_BBPDismantling_WL | EOSEUL-RRU25-1739 |  |  | 14.9413 | 120.5059 | FTAP |  |  |  | PAMPANGA | Gutad, Floridablanca, Pampanga | FLORIDABLANCA
CHANGEOUT | NL134 | NL134_BBU+UMPTChangeout_WL | GUTADPAM_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1122 |  |  | 14.9413 | 120.5059 | FTAP |  |  |  | PAMPANGA | Gutad, Floridablanca, Pampanga | FLORIDABLANCA
| NL136 | NL136_1800MRRUDismantling+Migration_WL | LUBAO_1800MRRUDismantling+Migration_WL | EOSEUL-RRU25-0429 |  |  | 14.93 | 120.5916 | GT BAU |  |  |  | PAMPANGA | Macaspac lot, Gapan-Olongapo road, Balantacan, Lubao, Pampanga | LUBAO
CHANGEOUT | NL136 | NL136_BBU+UMPTChangeout_WL | LUBAO_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1183 |  |  | 14.93 | 120.5916 | GT BAU |  |  |  | PAMPANGA | Macaspac lot, Gapan-Olongapo road, Balantacan, Lubao, Pampanga | LUBAO
DISMANTLING | NL137 | NL137_2100MDismantling_WL | TCMCRSANROQUEARBOLLUBAPPAM_2100MDismantling_WL | LUBAO2 |  |  | 14.8999 | 120.5459 | MIDC |  |  |  | PAMPANGA | San Roque Arbol, Lubao, Pampanga | LUBAO
CHANGEOUT | NL137 | NL137_BBU+UMPTChangeout_WL | LUBAO2_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1184 |  |  | 14.8999 | 120.5459 | MIDC |  |  |  | PAMPANGA | San Roque Arbol, Lubao, Pampanga | LUBAO
EOS | NL137 | NL137_EOS_WL | TCMCRSANROQUEARBOLLUBAPPAM_EOS_WL | LUBAO2 |  |  | 14.8999 | 120.5459 | MIDC |  |  |  | PAMPANGA | San Roque Arbol, Lubao, Pampanga | LUBAO
DISMANTLING/MIGRATION | NL138 | NL138_BBUDismantling+Migration_WL | MACABEBE_BBUDismantling+Migration_WL | EOSEUL-RRU25-1192 |  |  | 14.9052 | 120.7153 | MIDC |  |  |  | PAMPANGA | Santa Rita (Pob.), Macabebe, Pampanga | MACABEBE
CHANGEOUT | NL139 | NL139_BBU+UMPTChangeout_WL | MAGALANG_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1198 |  |  | 15.2173 | 120.6571 | MIDC |  |  |  | PAMPANGA | San Pedro II, Magalang, Pampanga | MAGALANG
DISMANTLING | NL1412 | NL1412_BBPDismantling_WL | BANCALPAM_BBPDismantling_WL | EOSEUL-RRU25-1718 |  |  | 14.9536 | 120.6316 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Bancal, Guagua, Pampanga | GUAGUA | LEMUEL NILL MALTO
CHANGEOUT | NL1412 | NL1412_BBU+UMPTChangeout_WL | BANCALPAM_BBU+UMPTChangeout_WL | EOSEUL-RRU25-0985 |  |  | 14.9536 | 120.6316 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Bancal, Guagua, Pampanga | GUAGUA | LEMUEL NILL MALTO
DISMANTLING | NL1417 | NL1417_BBPDismantling_WL | BRAYAT_BBPDismantling_WL | EOSEUL-RRU25-1722 |  |  | 15.1553 | 120.7266 | FTAP |  |  |  | PAMPANGA | Gatiawin, Arayat, Pampanga | ARAYAT
CHANGEOUT | NL1417 | NL1417_BBU+UMPTChangeout_WL | BRAYAT_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1009 |  |  | 15.1553 | 120.7266 | FTAP |  |  |  | PAMPANGA | Gatiawin, Arayat, Pampanga | ARAYAT
DISMANTLING/MIGRATION | NL143 | NL143_BBUDismantling+Migration_WL | TCFGALAUGMEXICOPAM_BBUDismantling+Migration_WL | EOSEUL-RRU25-1449 |  |  | 15.0506 | 120.7521 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | San Isidro, Laug, Mexico, Pampanga | MEXICO | LEMUEL NILL MALTO
EOS | NL143 | NL143_EOS_WL | TCFGALAUGMEXICOPAM_EOS_WL | MEXICOWST |  |  | 15.0506 | 120.7521 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | San Isidro, Laug, Mexico, Pampanga | MEXICO | LEMUEL NILL MALTO
CHANGEOUT | NL144 | NL144_BBU+UMPTChangeout_WL | MIMOSA_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1226 |  |  | 15.1835 | 120.525 | GT BAU |  |  |  | PAMPANGA | Holiday Inn Resort Clarkfield Building, Clark Special Economic Zone, Clarkfield, Sapangbato, Angeles City, Pampanga | ANGELES CITY
EOS | NL145 | NL145_EOS_WL | MINALIN_EOS_WL | MINALIN |  |  | 14.9747 | 120.6883 | MIDC |  |  |  | PAMPANGA | San Pedro, Minalin, Pampanga | MINALIN
DISMANTLING/MIGRATION | NL1475 | NL1475_BBUDismantling+Migration_WL | NICOLSPM_BBUDismantling+Migration_WL | EOSEUL-RRU25-1250 |  |  | 15.0181 | 120.7014 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Front of Camp Olivas, San Nicolas, San Fernando, Pampanga | CITY OF SAN FERNANDO | LEMUEL NILL MALTO
CHANGEOUT | NL148 | NL148_BBU+UMPTChangeout_WL | POBPORACPAM_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1290 |  |  | 15.0701 | 120.5346 | FOR TAGGING |  |  |  | PAMPANGA | M.L.Lapid Compound, Babo Pangulo, Porac, Pampanga | PORAC
| NL151 | NL151_BBPDismantling_WL | ROBINPAM_BBPDismantling_WL | EOSEUL-RRU25-1987 |  |  | 15.0495 | 120.6983 | GT BAU |  |  |  | PAMPANGA | Robinsons Pampanga, Olongapo-Gapan Road, Dolores, San Fernando, Pampanga | CITY OF SAN FERNANDO
| NL152 | NL152_1800MRRUDismantling+Migration_WL | SNFERNEST_1800MRRUDismantling+Migration_WL | EOSEUL-RRU25-0318 |  |  | 15.0113 | 120.7088 | GT BAU |  |  |  | PAMPANGA | Mc Arthur hi-way, San Matias, Santo Tomas, Pampanga | CITY OF SAN FERNANDO
| NL152 | NL152_G18_WL_TRX Downgrade | SNFERNEST_G18_WL_TRX Downgrade | EOSEUL-RRU25-0756 |  |  | 15.0113 | 120.7088 | GT BAU |  |  |  | PAMPANGA | Mc Arthur hi-way, San Matias, Santo Tomas, Pampanga | CITY OF SAN FERNANDO
| NL1536 | NL1536_BBPDismantling_WL | TCFGASANVICENTEGUAGUAPAM_BBPDismantling_WL | EOSEUL-RRU25-1812 |  |  | 15.0089 | 120.568 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | San Vicente (Ibus), Guagua, Pampanga | GUAGUA | LEMUEL NILL MALTO
EOS | NL1536 | NL1536_EOS_WL | TCFGASANVICENTEGUAGUAPAM_EOS_WL | PULUNGMASLE |  |  | 15.0089 | 120.568 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | San Vicente (Ibus), Guagua, Pampanga | GUAGUA | LEMUEL NILL MALTO
| NL154 | NL154_1800MDismantling_WL | TCFGASANNICOLASIMONPAM_1800MDismantling_WL | SANICOLAS |  |  | 15.0147 | 120.7804 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | San Nicolas, San Simon, Pampanga | SAN SIMON | LEMUEL NILL MALTO
| NL154 | NL154_BBPDismantling_WL | TCFGASANNICOLASIMONPAM_BBPDismantling_WL | EOSEUL-RRU25-1671 |  |  | 15.0147 | 120.7804 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | San Nicolas, San Simon, Pampanga | SAN SIMON | LEMUEL NILL MALTO
| NL154 | NL154_BBU+UMPTChangeout_WL | TCFGASANNICOLASIMONPAM_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1495 |  |  | 15.0147 | 120.7804 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | San Nicolas, San Simon, Pampanga | SAN SIMON | LEMUEL NILL MALTO
EOS | NL154 | NL154_EOS_WL | TCFGASANNICOLASIMONPAM_EOS_WL | SANICOLAS |  |  | 15.0147 | 120.7804 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | San Nicolas, San Simon, Pampanga | SAN SIMON | LEMUEL NILL MALTO
| NL154 | NL154_G9_WL_TRX Downgrade | TCFGASANNICOLASIMONPAM_G9_WL_TRX Downgrade | SANICOLAS |  |  | 15.0147 | 120.7804 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | San Nicolas, San Simon, Pampanga | SAN SIMON | LEMUEL NILL MALTO
| NL155 | NL155_BBUDismantling+Migration_WL | TCMCRSTONINOSIMONPAM_BBUDismantling+Migration_WL | EOSEUL-RRU25-1549 |  |  | 14.9867 | 120.7643 | MIDC |  |  |  | PAMPANGA | Santa Monica, San Simon, Pampanga | SAN SIMON
DISMANTLING/MIGRATION | NL156 | NL156_1800MRRUDismantling+Migration_WL | SNTLANGEL_1800MRRUDismantling+Migration_WL | EOSEUL-RRU25-0321 |  |  | 15.1579 | 120.5651 | GT BAU |  |  |  | PAMPANGA | Blk 17, Lot 4, 7th St.., Amsic, Angeles City, Pampanga | ANGELES CITY
| NL157 | NL157_BBPDismantling_WL | SASMUANLEG_BBPDismantling_WL | EOSEUL-RRU25-1782 |  |  | 14.9337 | 120.6243 | GT BAU |  |  |  | PAMPANGA | Santa Lucia (Pob.), Sasmuan (Sexmoan), Pampanga | SASMUAN
| NL157 | NL157_UMPTChangeOut_WL | SASMUANLEG_UMPTChangeOut_WL | EOSEUL-RRU25-1328 |  |  | 14.9337 | 120.6243 | GT BAU |  |  |  | PAMPANGA | Santa Lucia (Pob.), Sasmuan (Sexmoan), Pampanga | SASMUAN
| NL163 | NL163_2100MDismantling_WL | TCFGASANTACRUZLUBAPPAM_2100MDismantling_WL | STCRZLUBAO |  |  | 14.9082 | 120.5856 | FTAP |  |  |  | PAMPANGA | San Jose Gumi, Lubao, Pampanga | LUBAO
| NL163 | NL163_BBPDismantling_WL | TCFGASANTACRUZLUBAPPAM_BBPDismantling_WL | EOSEUL-RRU25-1810 |  |  | 14.9082 | 120.5856 | FTAP |  |  |  | PAMPANGA | San Jose Gumi, Lubao, Pampanga | LUBAO
| NL163 | NL163_BBUDismantling+Migration_WL | TCFGASANTACRUZLUBAPPAM_BBUDismantling+Migration_WL | EOSEUL-RRU25-1496 |  |  | 14.9082 | 120.5856 | FTAP |  |  |  | PAMPANGA | San Jose Gumi, Lubao, Pampanga | LUBAO
EOS | NL163 | NL163_EOS_WL | TCFGASANTACRUZLUBAPPAM_EOS_WL | STCRZLUBAO |  |  | 14.9082 | 120.5856 | FTAP |  |  |  | PAMPANGA | San Jose Gumi, Lubao, Pampanga | LUBAO
| NL165 | NL165_1800MRRUDismantling+Migration_WL | STANAPAMP_1800MRRUDismantling+Migration_WL | EOSEUL-RRU25-0324 |  |  | 15.0921 | 120.7777 | GT BAU |  |  |  | PAMPANGA | Santa Lucia, Santa Ana, Pampanga | STA ANA
| NL165 | NL165_BBPDismantling_WL | STANAPAMP_BBPDismantling_WL | EOSEUL-RRU25-1673 |  |  | 15.0921 | 120.7777 | GT BAU |  |  |  | PAMPANGA | Santa Lucia, Santa Ana, Pampanga | STA ANA
| NL165 | NL165_BBUDismantling+Migration_WL | STANAPAMP_BBUDismantling+Migration_WL | EOSEUL-RRU25-1363 |  |  | 15.0921 | 120.7777 | GT BAU |  |  |  | PAMPANGA | Santa Lucia, Santa Ana, Pampanga | STA ANA
| NL165 | NL165_G18_WL_TRX Downgrade | STANAPAMP_G18_WL_TRX Downgrade | EOSEUL-RRU25-0758 |  |  | 15.0921 | 120.7777 | GT BAU |  |  |  | PAMPANGA | Santa Lucia, Santa Ana, Pampanga | STA ANA
| NL166 | NL166_BBPDismantling_WL | STDOMINAL_BBPDismantling_WL | EOSEUL-RRU25-1792 |  |  | 14.9964 | 120.738 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Mc Arthur Hi-way, Santo Domingo, Minalin, Pampanga | CITY OF SAN FERNANDO | LEMUEL NILL MALTO
| NL166 | NL166_BBU+UMPTChangeout_WL | STDOMINAL_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1367 |  |  | 14.9964 | 120.738 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Mc Arthur Hi-way, Santo Domingo, Minalin, Pampanga | CITY OF SAN FERNANDO | LEMUEL NILL MALTO
EOS | NL167 | NL167_EOS_WL | TCFGASTOROSARIOMGLANGPAM_EOS_WL | STOROPAM |  |  | 15.2416 | 120.6366 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Santo Rosario, Magalang, Pampanga | MABALACAT CITY | EDGAR AQUINO / LEMUEL NILL MALTO
| NL168 | NL168_BBPDismantling_WL | SUCLAYIN_BBPDismantling_WL | EOSEUL-RRU25-1793 |  |  | 15.1699 | 120.7971 | FTAP |  |  |  | PAMPANGA | Suclayin, Arayat, Pampanga | ARAYAT
| NL168 | NL168_BBUDismantling+Migration_WL | SUCLAYIN_BBUDismantling+Migration_WL | EOSEUL-RRU25-1371 |  |  | 15.1699 | 120.7971 | FTAP |  |  |  | PAMPANGA | Suclayin, Arayat, Pampanga | ARAYAT
EOS | NL168 | NL168_EOS_WL | SUCLAYIN_EOS_WL | SUCLAYIN |  |  | 15.1699 | 120.7971 | FTAP |  |  |  | PAMPANGA | Suclayin, Arayat, Pampanga | ARAYAT
| NL168 | NL168_G9_WL_TRX Downgrade | SUCLAYIN_G9_WL_TRX Downgrade | SUCLAYIN |  |  | 15.1699 | 120.7971 | FTAP |  |  |  | PAMPANGA | Suclayin, Arayat, Pampanga | ARAYAT
| NL1686 | NL1686_BBPDismantling_WL | TCFGASANMATEOARAYATPAM_BBPDismantling_WL | EOSEUL-RRU25-1809 |  |  | 15.1948 | 120.8022 | FTAP |  |  |  | PAMPANGA | San Mateo, Arayat, Pampanga | ARAYAT
| NL1686 | NL1686_BBU+UMPTChangeout_WL | TCFGASANMATEOARAYATPAM_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1493 |  |  | 15.1948 | 120.8022 | FTAP |  |  |  | PAMPANGA | San Mateo, Arayat, Pampanga | ARAYAT
DISMANTLING | NL1699 | NL1699_BBPDismantling_WL | TCFGAANUNASANGELSPAM_BBPDismantling_WL | EOSEUL-RRU25-1676 |  |  | 15.1602 | 120.5495 | FTAP | APPLIED | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Purok 1, Fields Ave., Anunas, Angeles City, Pampanga | ANGELES CITY | EDGAR AQUINO / LEMUEL NILL MALTO
| NL1711 | NL1711_1800MRRUDismantling+Migration_WL | SNICOLPAM_1800MRRUDismantling+Migration_WL | EOSEUL-RRU25-0327 |  |  | 15.1252 | 120.7727 | FTAP |  |  |  | PAMPANGA | Rosita St., San Nicolas, Arayat, Pampanga | ARAYAT
| NL1711 | NL1711_BBU+UMPTChangeout_WL | SNICOLPAM_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1354 |  |  | 15.1252 | 120.7727 | FTAP |  |  |  | PAMPANGA | Rosita St., San Nicolas, Arayat, Pampanga | ARAYAT
EOS | NL173 | NL173_EOS_WL | TCFGAMANDILI2CNDABAPAM_EOS_WL | MANDILI |  |  | 15.1698 | 120.9143 | FTAP |  |  |  | PAMPANGA | Mandili, Candaba, Pampanga | CANDABA
| NL173 | NL173_G9_WL_TRX Downgrade | TCFGAMANDILI2CNDABAPAM_G9_WL_TRX Downgrade | MANDILI |  |  | 15.1698 | 120.9143 | FTAP |  |  |  | PAMPANGA | Mandili, Candaba, Pampanga | CANDABA
EOS | NL1743 | NL1743_EOS_WL | LAGUNDI_EOS_WL | LAGUNDI |  |  | 15.0564 | 120.7139 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Dolores, San Fernando, Pampanga | MEXICO | LEMUEL NILL MALTO
| NL1754 | NL1754_EOS_2023_WL | FLORIDPAM_EOS_WL | FLORIDPAM |  |  | 15.0052 | 120.5364 | FTAP |  |  |  | PAMPANGA | Pasvile Duhat, Pulungmasle, Guagua, Pampanga | FLORIDABLANCA
DISMANTLING | NL1833 | NL1833_BBPDismantling_WL | BALUBAD_BBPDismantling_WL | EOSEUL-RRU25-1714 |  |  | 15.0304 | 120.5435 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | David Lot, Mekeni Food Corp, Purok 3, Balubad, Porac, Pampanga | PORAC | EDGAR AQUINO / LEMUEL NILL MALTO
CHANGEOUT | NL1833 | NL1833_BBU+UMPTChangeout_WL | BALUBAD_BBU+UMPTChangeout_WL | EOSEUL-RRU25-0980 |  |  | 15.0304 | 120.5435 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | David Lot, Mekeni Food Corp, Purok 3, Balubad, Porac, Pampanga | PORAC | EDGAR AQUINO / LEMUEL NILL MALTO
| NL2019 | NL2019_2100MDismantling_WL | SJOSEFLPAM_2100MDismantling_WL | SJOSEFLPAM |  |  | 15.0152 | 120.4734 | FTAP |  |  |  | PAMPANGA | San Jose, Floridablanca, Pampanga | FLORIDABLANCA
| NL2030 | NL2030_BBPDismantling_WL | MAIMPISPAM_BBPDismantling_WL | EOSEUL-RRU25-1755 |  |  | 15.0716 | 120.6663 | MIDC |  |  |  | PAMPANGA | Miranda Bukid, Maimpis, City of San Fernando, Pampanga | CITY OF SAN FERNANDO
| NL2030 | NL2030_BBU+UMPTChangeout_WL | MAIMPISPAM_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1202 |  |  | 15.0716 | 120.6663 | MIDC |  |  |  | PAMPANGA | Miranda Bukid, Maimpis, City of San Fernando, Pampanga | CITY OF SAN FERNANDO
| NL2042 | NL2042_BBPDismantling_WL | KAMUNINGPAM_BBPDismantling_WL | EOSEUL-RRU25-1743 |  |  | 15.1175 | 120.6562 | MIDC |  |  |  | PAMPANGA | Camuning, Mexico, Pampanga | MEXICO
| NL2042 | NL2042_BBU+UMPTChangeout_WL | KAMUNINGPAM_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1154 |  |  | 15.1175 | 120.6562 | MIDC |  |  |  | PAMPANGA | Camuning, Mexico, Pampanga | MEXICO
DISMANTLING | NL2046 | NL2046_BBPDismantling_WL | TCMCRCAPAYAANGELSPAM_BBPDismantling_WL | EOSEUL-RRU25-1814 |  |  | 15.1446 | 120.6246 | MIDC |  |  |  | PAMPANGA | Capaya, Angeles City, Pampanga | ANGELES CITY
EOS | NL2046 | NL2046_EOS_WL | TCMCRCAPAYAANGELSPAM_EOS_WL | CAPAYANPAM |  |  | 15.1446 | 120.6246 | MIDC |  |  |  | PAMPANGA | Capaya, Angeles City, Pampanga | ANGELES CITY
| NL2066 | NL2066_BBPDismantling_WL | MIHILYPAM_BBPDismantling_WL | EOSEUL-RRU25-1953 |  |  | 15.0723 | 120.683 | MIDC |  |  |  | PAMPANGA | Malpitic_San Fernando City_Pampanga_P08_02, Malpitic, San Fernando, Pampanga | CITY OF SAN FERNANDO
| NL2067 | NL2067_BBPDismantling_WL | DELAPAZSIM_BBPDismantling_WL | EOSEUL-RRU25-1729 |  |  | 15.0246 | 120.7296 | MIDC |  |  |  | PAMPANGA | De La Paz, San Simon, Pampanga | SAN SIMON
| NL2067 | NL2067_BBU+UMPTChangeout_WL | DELAPAZSIM_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1073 |  |  | 15.0246 | 120.7296 | MIDC |  |  |  | PAMPANGA | De La Paz, San Simon, Pampanga | SAN SIMON
| NL2118 | NL2118_BBPDismantling_WL | TCMCRPANIPUANSFERNPAM_BBPDismantling_WL | EOSEUL-RRU25-1818 |  |  | 15.115 | 120.638 | MIDC |  |  |  | PAMPANGA | Purok 6, Panipuan, San Fernando, Pampanga | CITY OF SAN FERNANDO
| NL2118 | NL2118_BBUDismantling+Migration_WL | TCMCRPANIPUANSFERNPAM_BBUDismantling+Migration_WL | EOSEUL-RRU25-1539 |  |  | 15.115 | 120.638 | MIDC |  |  |  | PAMPANGA | Purok 6, Panipuan, San Fernando, Pampanga | CITY OF SAN FERNANDO
| NL2119 | NL2119_BBUDismantling+Migration_WL | CALULUTPAM_BBUDismantling+Migration_WL | EOSEUL-RRU25-1030 |  |  | 15.0982 | 120.6681 | MIDC |  |  |  | PAMPANGA | Calulut_San Fernando City_Pampanga | CITY OF SAN FERNANDO
| NL2145 | NL2145_BBPDismantling_WL | TCMCRTANGLEMEXICOPAM_BBPDismantling_WL | EOSEUL-RRU25-1822 |  |  | 15.1701 | 120.6491 | MIDC |  |  |  | PAMPANGA | Bo. Suarez, Brgy. Buenavista, Tangle (Tanglay), Mexico, Pampanga | MEXICO
DISMANTLING | NL2174 | NL2174_BBPDismantling_WL | R3FONTANA_BBPDismantling_WL | EOSEUL-RRU25-1984 |  |  | 15.194 | 120.5097 | GT BAU |  |  |  | PAMPANGA | R3 Bldg, Fontana Hotspring and Leisure Park, Pulung Maragul, Angeles City, Pampanga | ANGELES CITY
EOS | NL2204 | NL2204_EOS_WL | TCMCRINARAROPORACPAM_EOS_WL | BPANGULOPAM |  |  | 15.0829 | 120.512 | MIDC |  |  |  | PAMPANGA | Babo Pangulo, Porac, Pampanga | PORAC
EOS | NL2205 | NL2205_EOS_WL | SANRAMONPAM_EOS_WL | SANRAMONPAM |  |  | 14.997 | 120.4582 | FTAP |  |  |  | PAMPANGA | Brgy. San Ramon, Nabuclod, Floridablanca, Pampanga | LUBAO
| NL2294 | NL2294_1800MRRUDismantling+Migration_WL | SANFERNANBYN_1800MRRUDismantling+Migration_WL | EOSEUL-RRU25-0323 |  |  | 15.0292 | 120.6926 | GT BAU |  |  |  | PAMPANGA | Reloc Sta. Monica Bldg., B. Mendoza St.,, Santo Rosario (Pob.), CITY OF SAN FERNANDO (Capital), PAMPANGA, , NL | CITY OF SAN FERNANDO
| NL2294 | NL2294_BBPDismantling_WL | SANFERNANBYN_BBPDismantling_WL | EOSEUL-RRU25-1672 |  |  | 15.0292 | 120.6926 | GT BAU |  |  |  | PAMPANGA | Reloc Sta. Monica Bldg., B. Mendoza St.,, Santo Rosario (Pob.), CITY OF SAN FERNANDO (Capital), PAMPANGA, , NL | CITY OF SAN FERNANDO
| NL2294 | NL2294_BBUDismantling+Migration_WL | SANFERNANBYN_BBUDismantling+Migration_WL | EOSEUL-RRU25-1320 |  |  | 15.0292 | 120.6926 | GT BAU |  |  |  | PAMPANGA | Reloc Sta. Monica Bldg., B. Mendoza St.,, Santo Rosario (Pob.), CITY OF SAN FERNANDO (Capital), PAMPANGA, , NL | CITY OF SAN FERNANDO
DISMANTLING/MIGRATION | NL2381 | NL2381_BBUDismantling+Migration_WL | TABUNPAM_BBUDismantling+Migration_WL | EOSEUL-RRU25-1375 |  |  | 15.2501 | 120.565 | MIDC |  |  |  | PAMPANGA | BrgyCalumpang_Mabalacat_Pampanga, Calumpang, MABALACAT, PAMPANGA, REGION III (CENTRAL LUZON), NL | MABALACAT CITY
| NL2384 | NL2384_BBUDismantling+Migration_WL | PANDACRESPAM_BBUDismantling+Migration_WL | EOSEUL-RRU25-1267 |  |  | 15.1802 | 120.6492 | MIDC |  |  |  | PAMPANGA | William G. Kwongs Lot-, Pandacaqui, Mexico, Pampanga | MEXICO
EOS | NL2384 | NL2384_EOS_WL | PANDACRESPAM_EOS_WL | PANDACRESPAM |  |  | 15.1802 | 120.6492 | MIDC |  |  |  | PAMPANGA | William G. Kwongs Lot-, Pandacaqui, Mexico, Pampanga | MEXICO
| NL2387 | NL2387_BBPDismantling_WL | SJMALINOPAM_BBPDismantling_WL | EOSEUL-RRU25-1785 |  |  | 15.1292 | 120.6722 | FOR TAGGING |  |  |  | PAMPANGA | Sonny De Leons Lot- Purok 4, San Jose Malino, Mexico, Pampanga | MEXICO
| NL2387 | NL2387_BBUDismantling+Migration_WL | SJMALINOPAM_BBUDismantling+Migration_WL | EOSEUL-RRU25-1342 |  |  | 15.1292 | 120.6722 | FOR TAGGING |  |  |  | PAMPANGA | Sonny De Leons Lot- Purok 4, San Jose Malino, Mexico, Pampanga | MEXICO
| NL2401 | NL2401_BBPDismantling_WL | SANSIMONBYN_BBPDismantling_WL | EOSEUL-RRU25-1993 |  |  | 14.9993 | 120.7541 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Santa Monica, SAN SIMON, PAMPANGA, REGION III (CENTRAL LUZON), NL | SAN SIMON | LEMUEL NILL MALTO
| NL2446 | NL2446_UMPTChangeOut_WL | TCMCRSANAGUSTINARAYATPAM_UMPTChangeOut_WL | EOSEUL-RRU25-1545 |  |  | 15.1652 | 120.7792 | MIDC |  |  |  | PAMPANGA | Purok1, San Agustin Norte, Arayat, Pampanga | ARAYAT
| NL2450 | NL2450_BBU+UMPTChangeout_WL | TELAPAYONPAM_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1605 |  |  | 15.1923 | 120.6735 | MIDC |  |  |  | PAMPANGA | Telapayong, Arayat, Pampanga | ARAYAT
CHANGEOUT | NL2499 | NL2499_1800M+2100MRRUChangeout_WL | SMCLARKBPO_1800M+2100MRRUChangeout_WL | SMCLARKBPO |  |  | 15.1695 | 120.5786 | GT BAU |  |  |  | PAMPANGA | SM Clark Manuel A Roxas Highway, Balibago, ANGELES CITY, PAMPANGA, REGION III (CENTRAL LUZON), NL | ANGELES CITY
| NL66 | NL66_2100MDismantling_WL | TCFGAMAGSAYSAYGUAGUAPAM_2100MDismantling_WL | MAGSAYSAY |  |  | 14.981 | 120.5838 | FTAP |  |  |  | PAMPANGA | Magsaysay, Guagua, Pampanga | LUBAO
| NL66 | NL66_BBUDismantling+Migration_WL | TCFGAMAGSAYSAYGUAGUAPAM_BBUDismantling+Migration_WL | EOSEUL-RRU25-1455 |  |  | 14.981 | 120.5838 | FTAP |  |  |  | PAMPANGA | Magsaysay, Guagua, Pampanga | LUBAO
EOS | NL66 | NL66_EOS_WL | TCFGAMAGSAYSAYGUAGUAPAM_EOS_WL | MAGSAYSAY |  |  | 14.981 | 120.5838 | FTAP |  |  |  | PAMPANGA | Magsaysay, Guagua, Pampanga | LUBAO
| NL69 | NL69_BBPDismantling_WL | TCFGASANTAINESBCOLORPAM_BBPDismantling_WL | EOSEUL-RRU25-1680 |  |  | 14.9942 | 120.6553 | FTAP |  |  |  | PAMPANGA | Fajardo St., Santa Ines, Bacolor, Pampanga | BACOLOR
| NL69 | NL69_BBUDismantling+Migration_WL | TCFGASANTAINESBCOLORPAM_BBUDismantling+Migration_WL | EOSEUL-RRU25-1497 |  |  | 14.9942 | 120.6553 | FTAP |  |  |  | PAMPANGA | Fajardo St., Santa Ines, Bacolor, Pampanga | BACOLOR
EOS | NL70 | NL70_EOS_WL | TCFGASANILDEFONSOMGLANGPAM_EOS_WL | BALITPAM |  |  | 15.2582 | 120.7138 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Ayala, Magalang, Pampanga | MAGALANG | EDGAR AQUINO / LEMUEL NILL MALTO
| NL71 | NL71_2100MDismantling_WL | TCFGABALUCUCAPALITPAM_2100MDismantling_WL | BALUCOC |  |  | 14.9524 | 120.8216 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Brgy. Batasan Banag, Balucuc, Apalit, Pampanga | APALIT | LEMUEL NILL MALTO
EOS | NL71 | NL71_EOS_WL | TCFGABALUCUCAPALITPAM_EOS_WL | BALUCOC |  |  | 14.9524 | 120.8216 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Brgy. Batasan Banag, Balucuc, Apalit, Pampanga | APALIT | LEMUEL NILL MALTO
| NL71 | NL71_G9_WL_TRX Downgrade | TCFGABALUCUCAPALITPAM_G9_WL_TRX Downgrade | BALUCOC |  |  | 14.9524 | 120.8216 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Brgy. Batasan Banag, Balucuc, Apalit, Pampanga | APALIT | LEMUEL NILL MALTO
| NL72 | NL72_1800MRRUDismantling+Migration_WL | TCFGAAPALITFLORIDPAM_1800MRRUDismantling+Migration_WL | EOSEUL-RRU25-0419 |  |  | 14.9758 | 120.4803 | FTAP |  |  |  | PAMPANGA | Basa Airbase, Apalit, Floridablanca, Pampanga | FLORIDABLANCA
| NL75 | NL75_2100MDismantling_WL | CALUBASA_2100MDismantling_WL | CALUBASA |  |  | 15.1451 | 120.6518 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Culubasa, Mexico, Pampanga | MEXICO | LEMUEL NILL MALTO
| NL76 | NL76_2100MDismantling_WL | DELCARMEN_2100MDismantling_WL | DELCARMEN |  |  | 14.9372 | 120.5491 | FTAP |  |  |  | PAMPANGA | 128 Purok5, Del Carmen, Lubao, Pampanga | LUBAO
| NL76 | NL76_BBPDismantling_WL | DELCARMEN_BBPDismantling_WL | EOSEUL-RRU25-1730 |  |  | 14.9372 | 120.5491 | FTAP |  |  |  | PAMPANGA | 128 Purok5, Del Carmen, Lubao, Pampanga | LUBAO
| NL76 | NL76_BBUDismantling+Migration_WL | DELCARMEN_BBUDismantling+Migration_WL | EOSEUL-RRU25-1074 |  |  | 14.9372 | 120.5491 | FTAP |  |  |  | PAMPANGA | 128 Purok5, Del Carmen, Lubao, Pampanga | LUBAO
DISMANTLING | NL78 | NL78_BBPDismantling_WL | ISIDRODAU_BBPDismantling_WL | EOSEUL-RRU25-1906 |  |  | 15.1806 | 120.5912 | GT BAU |  |  |  | PAMPANGA | Brgy Village, Dau, Mabalacat, Pampanga | MABALACAT CITY
| NL80 | NL80_BBPDismantling_WL | JUANMEXI_BBPDismantling_WL | EOSEUL-RRU25-1742 |  |  | 15.1176 | 120.6986 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | San Juan, Mexico, Pampanga | MEXICO | LEMUEL NILL MALTO
| NL80 | NL80_BBU+UMPTChangeout_WL | JUANMEXI_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1147 |  |  | 15.1176 | 120.6986 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | San Juan, Mexico, Pampanga | MEXICO | LEMUEL NILL MALTO
| NL82 | NL82_BBPDismantling_WL | TCFGALANANGCNDABAPAM_BBPDismantling_WL | EOSEUL-RRU25-1796 |  |  | 15.1116 | 120.7899 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Lanang, Candaba, Pampanga | STA ANA | LEMUEL NILL MALTO
| NL84 | NL84_BBPDismantling_WL | TCFGASANFRANCISCOLUBAPPAM_BBPDismantling_WL | EOSEUL-RRU25-1808 |  |  | 14.9619 | 120.5466 | FTAP |  |  |  | PAMPANGA | Sitio Tramo, San Francisco, Lubao, Pampanga | LUBAO
| NL84 | NL84_BBU+UMPTChangeout_WL | TCFGASANFRANCISCOLUBAPPAM_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1490 |  |  | 14.9619 | 120.5466 | FTAP |  |  |  | PAMPANGA | Sitio Tramo, San Francisco, Lubao, Pampanga | LUBAO
| NL85 | NL85_BBPDismantling_WL | MACABEWST_BBPDismantling_WL | EOSEUL-RRU25-1754 |  |  | 14.908 | 120.6873 | FTAP |  |  |  | PAMPANGA | San Jose, Macabebe, Pampanga | MACABEBE
| NL85 | NL85_BBU+UMPTChangeout_WL | MACABEWST_BBU+UMPTChangeout_WL | EOSEUL-RRU25-1193 |  |  | 14.908 | 120.6873 | FTAP |  |  |  | PAMPANGA | San Jose, Macabebe, Pampanga | MACABEBE
| NL86 | NL86_BBUDismantling+Migration_WL | MANGGACAN_BBUDismantling+Migration_WL | EOSEUL-RRU25-1207 |  |  | 15.0168 | 120.8697 | FTAP |  |  |  | PAMPANGA | Barit, Candaba, Pampanga | CANDABA
| NL87 | NL87_BBPDismantling_WL | MARINGIN_BBPDismantling_WL | EOSEUL-RRU25-1946 |  |  | 15.0746 | 120.7787 | FTAP |  |  | EMAILED | PAMPANGA | Maringin St, Santa Maria, Santa Ana, Pampanga | STA ANA | LEMUEL NILL MALTO
| NL89 | NL89_BBPDismantling_WL | TCFGABEBEANACMSNTOLPAM_BBPDismantling_WL | EOSEUL-RRU25-1682 |  |  | 14.8804 | 120.7061 | FTAP |  |  |  | PAMPANGA | Bebe Anac, Masantol, Pampanga | MASANTOL
| NL89 | NL89_BBUDismantling+Migration_WL | TCFGABEBEANACMSNTOLPAM_BBUDismantling+Migration_WL | EOSEUL-RRU25-1407 |  |  | 14.8804 | 120.7061 | FTAP |  |  |  | PAMPANGA | Bebe Anac, Masantol, Pampanga | MASANTOL
DISMANTLING/MIGRATION | NL91 | NL91_BBUDismantling+Migration_WL | PANDACAQ_BBUDismantling+Migration_WL | EOSEUL-RRU25-1266 |  |  | 15.1902 | 120.6419 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Pandacaqui Resettlement, San Pedro I, Magalang, Pampanga | MAGALANG | EDGAR AQUINO / LEMUEL NILL MALTO
| NL92 | NL92_BBPDismantling_WL | PARICAND_BBPDismantling_WL | EOSEUL-RRU25-1771 |  |  | 15.0352 | 120.8811 | FTAP |  |  |  | PAMPANGA | Bahay Pare, Candaba, Pampanga | CANDABA
DISMANTLING | NL93 | NL93_BBPDismantling_WL | PORACBABO_BBPDismantling_WL | EOSEUL-RRU25-1973 |  |  | 15.0902 | 120.5344 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Cangatba, Porac, Pampanga | PORAC | EDGAR AQUINO / LEMUEL NILL MALTO
EOS | NL94 | NL94_EOS_WL | TCFGAMANIBAUGPASIGPORACPAM_EOS_WL | PORACNTH |  |  | 15.1104 | 120.5521 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Manibaug Libutad, Porac, Pampanga | PORAC | EDGAR AQUINO / LEMUEL NILL MALTO
DISMANTLING | NL95 | NL95_BBPDismantling_WL | TCFGAPLANASPORACPAM_BBPDismantling_WL | EOSEUL-RRU25-1803 |  |  | 15.0426 | 120.5121 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Planas, Porac, Pampanga | PORAC | EDGAR AQUINO / LEMUEL NILL MALTO
DISMANTLING/MIGRATION | NL95 | NL95_BBUDismantling+Migration_WL | TCFGAPLANASPORACPAM_BBUDismantling+Migration_WL | EOSEUL-RRU25-1477 |  |  | 15.0426 | 120.5121 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Planas, Porac, Pampanga | PORAC | EDGAR AQUINO / LEMUEL NILL MALTO
| NL97 | NL97_1800MDismantling_WL | SNLUISPAM_1800MDismantling_WL | SNLUISPAM |  |  | 15.0401 | 120.789 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Sn Luis Town Proper, Santa Cruz Poblacion, San Luis, Pampanga | SAN LUIS | LEMUEL NILL MALTO
EOS | NL97 | NL97_EOS_WL | SNLUISPAM_EOS_WL | SNLUISPAM |  |  | 15.0401 | 120.789 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | Sn Luis Town Proper, Santa Cruz Poblacion, San Luis, Pampanga | SAN LUIS | LEMUEL NILL MALTO
| NL99 | NL99_2100MDismantling_WL | TCFGASABANILLAMEXICOPAM_2100MDismantling_WL | SNMIGMEXPAM |  |  | 15.0731 | 120.6959 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | San Miguel, Mexico, Pampanga | MEXICO | LEMUEL NILL MALTO
EOS | NL99 | NL99_EOS_WL | TCFGASABANILLAMEXICOPAM_EOS_WL | SNMIGMEXPAM |  |  | 15.0731 | 120.6959 | FTAP |  | March 2 - March 17, 2026 | EMAILED | PAMPANGA | San Miguel, Mexico, Pampanga | MEXICO | LEMUEL NILL MALTO

## Sheet3
TERRITORY | PLA ID | DU ID | DU Name | MDB Province | OnAir Plan V2. | MUNICIPALITY
T2 | NL2807_NR26_64T64R_WL | BULACSMARIABUL_NR26_64T64R_WL | BULACSMARIABUL | BULACAN | 2025;(11) NOV | STA MARIA
T2 | NL2781_NR26_4T4R_WL | TCCRELOURDESSUBDPLARIDBUL_NR26_4T4R_WL | TCCRELOURDESSUBDPLARIDBUL | BULACAN | 2025;(11) NOV | PLARIDEL
T2 | NL544_NR26_64T64R_WL | TABANGPLARIDBUL_NR26_64T64R_WL | PLARIDEL | BULACAN | 2025;(11) NOV | PLARIDEL
T2 | NL2777_NR35_WL | TCCREPRENZA1MRILAOBUL_NR35_WL | TCCREPRENZA1MRILAOBUL | BULACAN | 2025;(11) NOV | MARILAO
T2 | NL5389_NR26_64T64R_WL_add sector | TCAICLOMADEGATO3MRILAOBUL_NR26_64T64R_WL_add sector | LOMADEGATO3MRILAOBUL | BULACAN | 2025;(12) DEC | MARILAO
T2 | NL2077_NR26_64T64R_40M_WL | TCMCRMOJONMLOLOSBUL_NR26_64T64R_40M_WL | MOJONBUL | BULACAN | 2025;(12) DEC | MALOLOS
T2 | NL315_NR26_64T64R_40M_WL | TCFGAPINAGBAKAHANMLOLOSBUL_NR26_64T64R_40M_WL | LOOKFIRST | BULACAN | 2025;(12) DEC | MALOLOS
T2 | NL545_NR26_64T64R_40M_WL | TCMCRSUMAPANGMTANDAMLOLOSBUL_NR26_64T64R_40M_WL | MALOLOS2 | BULACAN | 2025;(12) DEC | MALOLOS
T2 | NL594_NR26_64T64R_40M_WL | TCFGABALITEMLOLOSBUL_NR26_64T64R_40M_WL | MATIMBMAL | BULACAN | 2025;(12) DEC | MALOLOS
T2 | NL1522_EOS_WL | TCFGAHERITAGEMEYCAUBUL_EOS_WL | HERITAGEMEY | BULACAN | 2025;(12) DEC | MEYCAUAYAN
T2 | NL2230_1800MDismantling_WL | PH6ARENAID_1800MDismantling_WL | PH6ARENAID | BULACAN | 2025;(12) DEC | BOCAUE
T2 | NL2782_L700_WL | TCATCSANJOSEPLARIDBUL_L700_WL | TCATCSANJOSEPLARIDBUL | BULACAN | 2025;(10) OCT | PLARIDEL
T2 | NL2782_L900_WL | TCATCSANJOSEPLARIDBUL_L900_WL | TCATCSANJOSEPLARIDBUL | BULACAN | 2025;(10) OCT | PLARIDEL
T2 | NL545_EOS_WL | TCMCRSUMAPANGMTANDAMLOLOSBUL_EOS_WL | MALOLOS2 | BULACAN | 2025;(12) DEC | MALOLOS
T2 | NL545_G9_WL_TRX Downgrade | TCMCRSUMAPANGMTANDAMLOLOSBUL_G9_WL_TRX Downgrade | MALOLOS2 | BULACAN | 2025;(11) NOV | MALOLOS
T2 | NL570_EOS_WL | TCFGAPEREZMEYCAUBUL_EOS_WL | PEREZMEY | BULACAN | 2025;(12) DEC | MEYCUAYAN
T2 | NL573_700M+900MRRUChangeout_WL | LOMADEGATO1MRILAOBUL_700M+900MRRUChangeout_WL | LOMADEGATO1MRILAOBUL | BULACAN | 2025;(11) NOV | MARILAO
T2 | NL580_EOS_WL | TCFGASANVICENTESMARIABUL_EOS_WL | STAMAREAST | BULACAN | 2025;(11) NOV | STA MARIA
T2 | NL595_2_EOS_WL | TCFGADAMPOLPLARIDBUL_2_EOS_WL | PLARIDLAG | BULACAN | 2025;(11) NOV | PLARIDEL
T2 | NL595_EOS_WL | TCFGADAMPOLPLARIDBUL_EOS_WL | PLARIDLAG | BULACAN | 2025;(11) NOV | PLARIDEL
T2 | NL595_G9G18_WL_TRX Downgrade | TCFGADAMPOLPLARIDBUL_G9G18_WL_TRX Downgrade | PLARIDLAG | BULACAN | 2025;(10) OCT | PLARIDEL
NL145 | MINALIN |  | San Pedro, Minalin, Pampanga
NL2042 | KAMUNINGPAM | TCMCRCAMUNINGMEXICOPAM | Camuning, Mexico, Pampanga
NL2145 | TAGLEPAM | TCMCRTANGLEMEXICOPAM | Bo. Suarez, Brgy. Buenavista, Tangle (Tanglay), Mexico, Pampanga
NL2384 | PANDACRESPAM | 0 | William G. Kwongs Lot-, Pandacaqui, Mexico, Pampanga
NL2387 | SJMALINOPAM | 0 | Sonny De Leons Lot- Purok 4, San Jose Malino, Mexico, Pampanga